{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["作番大日程(汰改)","Worksheet"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"作番大日程(汰改)","index":0,"n_rows":106,"n_cols":55,"rows_kept":106,"cut":false,"hidden":false,"merged":[]}
["合約號","作番號","汰改方案","客戶名稱","地址","工地地址","規格","依合約客戶需求日","下單日(普來特富)","預計發貨日(普來特富)","預計到廠日(觀音廠)","實際到廠日(觀音廠)","預計出貨日(到工地)","工務確認","樓高通報","樓高通報日期","工勘確認","工勘確認日期","客戶計劃圖(意匠圖)","客戶計劃圖(意匠圖)日期","營業/契約確認","營業/契約規格","營業/契約規格日期","客戶顏色","客戶顏色日期","客戶樣式","客戶樣式日期","工勘聯絡表","工勘聯絡表日期","設計確認","設計規格","設計規格日期","設計計劃圖","設計計劃圖日期","設計顏色","設計顏色日期","設計樣式","設計樣式日期","設計主管","設計主管日期","生管確認","是否齊備","是否齊備日期","下單日(下單普來特富)","下單日(下單普來特富)日期","預計發貨日(出港日)","預計發貨日(出港日)日期","預計實際到貨日(到觀音廠日)","預計實際到貨日(到觀音廠日)日期","普來特富(發貨類別)","普來特富(發貨類別)日期","台灣自理項目(發貨類別)","台灣自理項目(發貨類別)日期","實際到貨日(到觀音廠日)","實際到貨日(到觀音廠日)日期"]
["M231018","3JX05001","MA","華娛文創行銷股份有限公司","屏東縣恆春鎮墾丁路312號",null,"MAE100-10-700-4/4-2S45","2023-10-16","2023-08-11","2023-11-20","2023-12-01",null,"2024-04-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","已完成","2023-08-11","進行中","2023-08-11","進行中","2023-11-20","進行中","2023-12-01","未確認",null,"未確認",null,"未確認"]
["D23080037","3JX06401","MA","黃麗紅","高雄市三民區大昌二路530號",null,"MAE100-8-550-8/8-2PCO60","2024-02-15",{"$nulls":4},"2024-02-15","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["T230005","3JX07401","MA","佛光山寺","高雄市大樹區興田路153號",null,"MAE100-12-1000-6/6-CO60","2024-01-31",{"$nulls":4},"2024-01-31","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07003","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07004","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07005","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07006","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07007","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07008","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07009","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07010","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07025","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90",{"$nulls":5},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認"]
["B23080083","3JX07040","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-10/10-CO90","2023-10-20",{"$nulls":4},"2024-01-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07030","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07031","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07032","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07033","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07034","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07035","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07036","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07037","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-10/10-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07038","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-10/10-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07039","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-10/10-CO90","2023-10-20",{"$nulls":4},"2024-01-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230226","3JX05101","M1","NEW STAR","高雄市岡山區忠誠街207號",null,"MAE100-15-1000-17/17-2PCO105","2023-10-25",{"$nulls":4},"2024-01-19","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230226","3JX05102","M1","NEW STAR","高雄市岡山區忠誠街207號",null,"MAE100-15-1000-17/17-2PCO105","2023-10-25",{"$nulls":4},"2024-01-19","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230226","3JX05103","M1","NEW STAR","高雄市岡山區忠誠街207號",null,"MAE100-15-1000-17/17-2PCO105","2023-10-25",{"$nulls":4},"2024-01-19","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230226","3JX05104","M1","NEW STAR","高雄市岡山區忠誠街207號",null,"MAE100-15-1000-17/17-2PCO105","2023-10-25",{"$nulls":4},"2024-01-19","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230226","3JX05105","M1","NEW STAR","高雄市岡山區忠誠街207號",null,"MAE100-15-1000-17/17-2PCO105","2023-10-25",{"$nulls":4},"2024-01-19","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230226","3JX05106","M1","NEW STAR","高雄市岡山區忠誠街207號",null,"MAE100-15-1000-17/17-2PCO105","2023-10-25",{"$nulls":4},"2024-01-19","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07019","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07020","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07021","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07022","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07023","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07024","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07026","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07027","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07028","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07029","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07001","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07002","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07011","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07012","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07013","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07014","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07015","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07016","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07017","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["B23080083","3JX07018","M1","君毅正勤社區管理委員會","高雄市前鎮區君毅正勤社區內",null,"MAE100-12-800-12/12-CO90","2023-10-20",{"$nulls":4},"2024-01-09","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["D23080159","3JX06801","MA","上新廚具行(8)","屏東鎮潮州鎮中正路17號",null,"MAE100-6-450-4/4-2PCO60","2023-12-31",{"$nulls":4},"2023-12-31","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"陳哲軒 0/4","進行中","2023-10-19","進行中","2023-09-25","進行中","2023-09-25","進行中","2023-09-25","林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["D23080046","3JX05801","MA","明誠殿廈","高雄市鼓山區華泰路218號",null,"MAE100-8-550-9/9-2PCO60","2023-12-01",{"$nulls":4},"2023-12-01","鄭存邑2/3","已完成","2023-10-16","已確認","2023-10-16","進行中",null,"陳哲軒 0/4","進行中","2023-10-03","進行中","2023-09-05","進行中","2023-09-05","進行中","2023-09-05","林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["D23080052","3JX05601","MA","順利建設","高雄市內門區永富里富田17-3號",null,"MAE100-8-550-3/3-2PCO45","2023-10-31","2023-10-11","2023-11-20","2023-11-30",null,"2023-11-30","鄭存邑2/3","已完成","2023-10-16","已確認","2023-10-16","無需求","2023-10-18","蔡家核 0/4","進行中","2023-10-11","進行中","2023-09-05","進行中","2023-09-05","進行中","2023-09-05","林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-11","進行中","2023-11-20","進行中","2023-11-30","未確認",null,"未確認",null,"未確認"]
["Q23090019","3JX06902","M1","文化錠管理委員會大樓","高雄市光華一路103號",null,"MAE100-12-800-20/20-2PCO105",null,"2023-10-11","2023-11-13","2023-11-30",null,"2023-11-30","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-11","進行中","2023-11-13","進行中","2023-11-30","未確認",null,"未確認",null,"未確認"]
["Q23090019","3JX06901","M1","文化錠管理委員會大樓","高雄市光華一路103號",null,"MAE100-12-800-20/20-2PCO105",null,"2023-10-11","2023-11-10","2023-11-23",null,"2023-11-23","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-11","進行中","2023-11-10","進行中","2023-11-23","未確認",null,"未確認",null,"未確認"]
["M230804","3JX05501","MA","光遠華廈","高雄市鳳山區光遠路263號",null,"MAE100-8-550-11/11-2PCO60","2023-10-31","2023-10-16","2023-11-03","2023-11-24",null,"2023-11-16","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中","2023-10-16","進行中","2023-09-05","進行中","2023-09-05","進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-16","進行中","2023-11-03","進行中","2023-11-24","未確認",null,"未確認",null,"未確認"]
["M230575","3JX05301","M1+M4","登輝美景大樓","高雄市三民區汾水路11號",null,"MAE100-8-550-9/9-2PCO60","2023-11-01","2023-10-06","2023-10-30","2023-11-15",null,"2023-11-15","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-06","進行中","2023-10-30","進行中","2023-11-15","未確認",null,"未確認",null,"未確認"]
["M230575","3JX05302","M1+M4","登輝美景大樓","高雄市三民區汾水路11號",null,"MAE100-8-550-10/10-2PCO60","2023-11-01","2023-10-06","2023-10-30","2023-11-15",null,"2023-11-15","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-06","進行中","2023-10-30","進行中","2023-11-15","未確認",null,"未確認",null,"未確認"]
["M230575","3JX05303","M1+M4","登輝美景大樓","高雄市三民區汾水路11號",null,"MAE100-8-550-10/10-2PCO60","2023-11-01","2023-10-06","2023-10-30","2023-11-15",null,"2023-11-15","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-06","進行中","2023-10-30","進行中","2023-11-15","未確認",null,"未確認",null,"未確認"]
["M230575","3JX05304","M1+M4","登輝美景大樓","高雄市三民區汾水路11號",null,"MAE100-8-550-11/11-2PCO60","2023-11-01","2023-10-06","2023-10-30","2023-11-15",null,"2023-11-15","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-10-06","進行中","2023-10-30","進行中","2023-11-15","未確認",null,"未確認",null,"未確認"]
["D23080018","3JX05401","M1","皇家彩國際企業有限公司","高雄市前金路中華三路103號1F",null,"MAH100-6-450-6/6-2S45","2023-10-18","2023-08-30","2023-09-25","2023-10-12",null,"2023-11-15","鄭存邑0/3","進行中","2023-10-16","未確認",null,"進行中",null,"蔡家核 0/4","進行中","2023-09-05","進行中","2023-09-05","進行中","2023-09-05","進行中","2023-09-05","林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-09-14","已完成","2023-08-30","進行中","2023-09-25","進行中","2023-10-12","未確認",null,"未確認",null,"未確認"]
["M230567","3JX05701","M1","四季香頌","高雄市楠梓區裕昌街153號",null,"MAE100-12-800-17/17-2PCO105","2023-10-31",{"$nulls":4},"2023-10-31","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡家核 0/4","進行中","2023-10-11","進行中","2023-10-07","進行中","2023-10-07","進行中","2023-10-07","林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]
["M230079","3JX00903","MA","財富邑","高雄市三民區建國二路2號",null,"MAE100-10-14-CO105","2023-08-20","2023-03-27","2023-05-23","2023-06-30","2023-06-08","2023-10-18","鄭存邑2/3","已完成","2023-10-17","已確認","2023-10-17","無需求","2023-10-17","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中","2023-03-27","進行中","2023-05-23","進行中","2023-06-30","未確認",null,"未確認",null,"A:皆到貨","2023-06-08"]
["M220275","2MX00036","MA","福震雙星花園大樓","高雄大寮區成功路116巷11-1號",null,"MAE100-12-16-CO90","2023-08-15","2023-02-16","2023-04-23","2023-03-31","2023-05-09","2023-10-13","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 7/7","已完成","2023-08-07","已完成","2023-02-16","已完成","2023-04-23","已完成","2023-03-31","C:無發貨需求",null,"C:無發貨需求",null,"A:皆到貨","2023-05-09"]
["M230469","3JX02504","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-18/18-2PCO105",null,"2023-08-22","2023-09-14","2023-09-29","2023-10-02","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-14","進行中","2023-09-29","未確認",null,"未確認",null,"未確認","2023-10-02"]
["M230469","3JX02505","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-22/22-2PCO105",null,"2023-08-22","2023-09-20","2023-10-11","2023-10-11","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-20","進行中","2023-10-11","未確認",null,"未確認",null,"未確認","2023-10-11"]
["M230469","3JX02506","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-22/22-2PCO105",null,"2023-08-22","2023-09-20","2023-10-11","2023-10-11","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-20","進行中","2023-10-11","未確認",null,"未確認",null,"未確認","2023-10-11"]
["M230469","3JX02507","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-22/22-2PCO105",null,"2023-08-22","2023-09-20","2023-10-11","2023-10-11","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-20","進行中","2023-10-11","未確認",null,"未確認",null,"未確認","2023-10-11"]
["M230469","3JX02508","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-18/18-2PCO105",null,"2023-08-22","2023-09-14","2023-09-29","2023-10-02","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-14","進行中","2023-09-29","未確認",null,"未確認",null,"未確認","2023-10-02"]
["M230469","3JX02509","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-18/18-2PCO105",null,"2023-08-22","2023-09-14","2023-09-29","2023-10-02","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-14","進行中","2023-09-29","未確認",null,"未確認",null,"未確認","2023-10-02"]
["M230469","3JX02510","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-22/22-2PCO105",null,"2023-08-22","2023-09-20","2023-10-11","2023-10-11","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-20","進行中","2023-10-11","未確認",null,"未確認",null,"未確認","2023-10-11"]
["M230469","3JX02511","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-22/22-2PCO105",null,"2023-08-22","2023-09-20","2023-09-29","2023-10-11","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-20","進行中","2023-09-29","未確認",null,"未確認",null,"未確認","2023-10-11"]
["M230469","3JX02512","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-22/22-2PCO105",null,"2023-08-22","2023-09-20","2023-10-03","2023-10-11","2023-10-13","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 2/7","已完成","2023-08-22","已完成","2023-08-22","進行中","2023-09-20","進行中","2023-10-03","未確認",null,"未確認",null,"未確認","2023-10-11"]
["M230079","3JX00902","MA","財富邑","高雄市三民區建國二路2號",null,"MAE100-10-14-CO105","2023-08-20","2023-03-27","2023-05-23","2023-06-30","2023-06-08","2023-09-26","鄭存邑2/3","已完成","2023-10-17","已確認","2023-10-17","無需求","2023-10-17","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中","2023-03-27","進行中","2023-05-23","進行中","2023-06-30","未確認",null,"未確認",null,"A:皆到貨","2023-06-08"]
["M230785","3JX4801","M1","莊景芳","屏東縣屏東市洛陽街",null,"MAH100-6-450-6/6-2PCO45","2023-08-30","2023-08-09",null,null,"2023-09-14","2023-09-21","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","已完成","2023-08-11","進行中","2023-08-09","進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-09-14"]
["M230650","3JX04501","M1","站前廣場","高雄市三民區建國三路20號",null,null,"2023-09-01","2023-08-10","2023-09-30","2023-09-10","2023-09-14","2023-09-14","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-08-10","進行中","2023-09-30","進行中","2023-09-10","未確認",null,"未確認",null,"未確認","2023-09-14"]
["M230650","3JX04502","M1","站前廣場","高雄市三民區建國三路20號",null,null,"2023-09-01","2023-08-10","2023-09-30","2023-09-10","2023-09-14","2023-09-14","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-08-10","進行中","2023-09-30","進行中","2023-09-10","未確認",null,"未確認",null,"未確認","2023-09-14"]
["M230650","3JX04503","M1","站前廣場","高雄市三民區建國三路20號",null,null,"2023-09-01","2023-08-10","2023-09-30","2023-09-10","2023-09-14","2023-09-14","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-08-10","進行中","2023-09-30","進行中","2023-09-10","未確認",null,"未確認",null,"未確認","2023-09-14"]
["M230650","3JX04504","M1","站前廣場","高雄市三民區建國三路20號",null,null,"2023-09-01","2023-08-10","2023-09-30","2023-09-10","2023-09-14","2023-09-14","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"羅仁聰 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-08-10","進行中","2023-09-30","進行中","2023-09-10","未確認",null,"未確認",null,"未確認","2023-09-14"]
["M230992","3JX04901","M1","瀚平世家","台南市東區崇德十八街108號",null,"MAE100-8-550-6/6-2PCO60","2023-08-15",null,null,null,"2023-08-16","2023-08-17","鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認","2023-08-16"]
["M230159","3JX00801","MA","皇朝尊龍","台南市安平區建平五街22巷15弄14號",null,"MAE100-11-7-CO60","2023-08-30",null,"2023-05-26",null,"2023-06-08","2023-08-14","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中",null,"進行中","2023-05-26","進行中",null,"未確認",null,"未確認",null,"A:皆到貨","2023-06-08"]
["M220275","2MX00030","MA","福震雙星花園大樓","高雄大寮區成功路116巷11-1號",null,"MAE100-12-16-CO90","2023-08-15","2023-02-16","2023-04-15","2023-03-31","2023-05-09","2023-08-09","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中","2023-02-16","進行中","2023-04-15","進行中","2023-03-31","未確認",null,"未確認",null,"A:皆到貨","2023-05-09"]
["M220275","2MX00032","MA","福震雙星花園大樓","高雄大寮區成功路116巷11-1號",null,"MAE100-12-16-CO90","2023-08-19","2023-02-16","2023-04-15","2023-03-31","2023-05-15","2023-08-09","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中","2023-02-16","進行中","2023-04-15","進行中","2023-03-31","未確認",null,"未確認",null,"A:皆到貨","2023-05-15"]
["M220275","2MX00035","MA","福震雙星花園大樓","高雄大寮區成功路116巷11-1號",null,"MAE100-12-16-CO90","2023-08-19","2023-02-16","2023-04-15","2023-03-31","2023-05-09","2023-08-09","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中","2023-02-16","進行中","2023-04-15","進行中","2023-03-31","未確認",null,"未確認",null,"A:皆到貨","2023-05-09"]
["M220275","2MX00034","MA","福震雙星花園大樓","高雄",null,"MAE100-12-16-CO90","2023-04-01","2023-02-16","2023-04-15","2023-03-31","2023-05-15","2023-08-03","鄭存邑3/3","已完成","2023-08-27","已確認","2023-08-27","已完成","2023-08-27","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-02-16","進行中","2023-04-15","進行中","2023-03-31","未確認",null,"未確認",null,"未確認","2023-05-15"]
["M230469","3JX02501","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-18/18-2PCO105",null,"2023-06-07","2023-07-12","2023-08-02","2023-07-18","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 5/7","已完成","2023-08-22","已完成","2023-06-07","已完成","2023-07-12","進行中","2023-08-02","A:全級發貨",null,"未確認",null,"A:皆到貨","2023-07-18"]
["M230469","3JX02502","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-18/18-2PCO105",null,"2023-06-07","2023-07-12","2023-08-02","2023-07-18","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 5/7","已完成","2023-08-22","已完成","2023-06-07","已完成","2023-07-12","進行中","2023-08-02","A:全級發貨",null,"未確認",null,"A:皆到貨","2023-07-18"]
["M230469","3JX02503","M1","悅誠","高雄市左營區鼓山三路383號",null,"MAE100-17-1150-18/18-2PCO105",null,"2023-06-07","2023-07-12","2023-08-02","2023-07-18","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","陳哲軒 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 6/7","已完成","2023-08-22","已完成","2023-06-07","已完成","2023-07-12","已完成","2023-08-02","A:全級發貨",null,"未確認",null,"A:皆到貨","2023-07-18"]
["M230304","3JX02803","M1","巨鎧科技","台南",null,null,"2023-06-30",null,null,null,"2023-07-14","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-07-14"]
["M230304","3JX02806","M1","巨鎧科技","台南",null,null,"2023-06-30",null,null,null,"2023-07-14","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-07-14"]
["M230304","3JX02807","M1","巨鎧科技","台南",null,null,"2023-06-30",null,null,null,"2023-07-14","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-07-14"]
["M230304","3JX02808","M1","巨鎧科技","台南",null,null,"2023-06-30",null,null,null,"2023-07-14","2023-07-25","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-07-14"]
["M230289","3JX01601","MA","金如意餐具","台南",null,"MAH100-6-5-2S45","2023-06-20",null,"2023-05-28",null,"2023-06-19","2023-07-07","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","蔡家核 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中","2023-05-28","進行中",null,"未確認",null,"未確認",null,"未確認","2023-06-19"]
["M230304","3JX02804","M1","巨鎧科技","台南",null,null,"2023-06-30",null,null,null,"2023-07-07","2023-07-07","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-07-07"]
["M230304","3JX02805","M1","巨鎧科技","台南",null,null,"2023-06-30",null,null,null,"2023-07-07","2023-07-07","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-07-07"]
["M230159","3JX00802","MA","皇朝尊龍","台南市安平區建平五街22巷15弄14號",null,"MAE100-11-7-CO60","2023-06-01",null,"2023-05-26",null,"2023-06-08","2023-06-20","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 1/7","進行中",null,"進行中",null,"進行中","2023-05-26","進行中",null,"未確認",null,"未確認",null,"A:皆到貨","2023-06-08"]
["M230079","3JX00901","MA","財富邑","高雄",null,"MAE100-10-14-CO105","2023-06-30",null,"2023-05-23",null,"2023-06-08","2023-06-20","鄭存邑2/3","已完成","2023-10-17","已確認","2023-10-17","無需求","2023-10-17","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中","2023-05-23","進行中",null,"未確認",null,"未確認",null,"未確認","2023-06-08"]
["M230304","3JX02801","M1","巨鎧科技","台南",null,null,"2023-06-05",null,null,null,"2023-06-05","2023-06-07","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-06-05"]
["M230304","3JX02802","M1","巨鎧科技","台南",null,null,"2023-06-05",null,null,null,"2023-06-05","2023-06-07","鄭存邑2/3","已完成","2023-10-18","已確認","2023-10-18","無需求","2023-10-18","張乃文 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",null,"未確認",null,"未確認",null,"未確認","2023-06-05"]
["M220275","2MX00037","MA","福震雙星花園大樓","高雄",null,"MAE100-12-16-CO90","2023-04-01","2023-02-16","2023-04-23","2023-03-31","2023-05-09","2023-05-31","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 7/7","已完成","2023-08-07","已完成","2023-02-16","已完成","2023-04-23","已完成","2023-03-31","C:無發貨需求",null,"C:無發貨需求",null,"A:皆到貨","2023-05-09"]
["M220275","2MX00031","MA","福震雙星花園大樓","高雄",null,"MAE100-12-16-CO90","2023-04-01","2023-02-16","2023-04-15","2023-03-31","2023-05-09","2023-05-15","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-02-16","進行中","2023-04-15","進行中","2023-03-31","未確認",null,"未確認",null,"未確認","2023-05-09"]
["M220275","2MX00033","MA","福震雙星花園大樓","高雄",null,"MAE100-12-16-CO90","2023-04-01","2023-02-16","2023-04-15","2023-03-31","2023-05-09","2023-05-12","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-02-16","進行中","2023-04-15","進行中","2023-03-31","未確認",null,"未確認",null,"未確認","2023-05-09"]
["M230068","3JX00301","M1","高雄金鹽埕","高雄",null,"MAE100-12-12-CO60","2023-03-01","2023-02-10","2023-02-27","2023-02-27","2023-03-23","2023-03-28","鄭存邑2/3","已完成","2023-10-16","已確認","2023-10-16","無需求","2023-10-17","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-02-10","進行中","2023-02-27","進行中","2023-02-27","未確認",null,"未確認",null,"未確認","2023-03-23"]
["M230068","3JX00302","M1","高雄金鹽埕","高雄",null,"MAE100-12-12-CO60","2023-03-01","2023-02-10","2023-02-27","2023-02-27","2023-03-23","2023-03-28","鄭存邑2/3","已完成","2023-10-16","已確認","2023-10-16","無需求","2023-10-17","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2023-02-10","進行中","2023-02-27","進行中","2023-02-27","未確認",null,"未確認",null,"未確認","2023-03-23"]
["M220275","2MX00029","MA","福震雙星花園大樓","高雄",null,"MAE100-12-16-CO90","2023-03-01","2022-12-30","2023-02-26","2023-02-15","2023-03-09","2023-03-15","鄭存邑2/3","已完成","2023-10-19","已確認","2023-10-19","無需求","2023-10-19","蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中","2022-12-30","進行中","2023-02-26","進行中","2023-02-15","未確認",null,"未確認",null,"未確認","2023-03-09"]
["M220422","3JX06604","M1","蔚藍海18","高雄市楠梓區大62街30號",null,"MAE100-12-800-19/19-2PCO105",{"$nulls":6},"鄭存邑0/3","進行中",null,"未確認",null,"進行中",null,"蔡守弦 0/4","進行中",null,"進行中",null,"進行中",null,"進行中",null,"林昭翰 0/5","進行中",null,"進行中",null,"進行中",null,"進行中",null,"進行中",null,"許伃廷 0/7","進行中",null,"進行中",null,"進行中",null,"進行中",{"$nulls":5},"未確認"]

{"sheet":"Worksheet","index":1,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["確認進度統計表"]