{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["工作表1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"工作表1","index":0,"n_rows":16,"n_cols":10,"rows_kept":16,"cut":false,"hidden":false,"merged":[[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,4],[1,5,2,5],[1,7,2,7],[1,8,1,9],[2,8,2,9],[3,1,3,2],[3,3,3,4],[3,7,3,9],[1,6,2,6],[0,0,0,9],[11,0,11,2],[12,0,12,2],[13,0,13,2],[7,0,7,2],[8,0,8,2],[9,0,9,2],[10,0,10,2],[6,3,13,6],[6,7,13,9],[4,1,4,2],[4,7,4,8],[5,0,5,2],[5,3,5,6],[5,7,5,9],[6,0,6,2]]}
["                                    工 地 勘 查 表                                    日期:112/01/03"]
["客戶名稱","鑲揚國際開發(左東段)","作番","M230810",null,"連絡對象","謝明哲主任","電話"]
[{"$nulls":8},"0986-617235"]
["地址","高雄市左營區左營大路672巷65號對面",null,"建築進度/樓",null,"8月動工","營業承辦人","杜孟釗"]
["規格","如下述備註",null,"電源","單相220V","罰款","有 74200/1天","預定交期",null,"112/12/15"]
["營業特記事項",null,null,"工勘確認事項",null,null,null,"電源確認客戶簽章"]
["規格:"]
["MAH100-6*4-2S45*28台(1-4F)"]
["有逾期罰緩,需100天內安裝完畢並取得電梯合格函"]
["因尚未動工,工地主任電話後補"]
["本案只有#23號機(D1戶)是左開"]
[]
[]
[]
[]
[{"$nulls":9},"版次：1.0"]